## Jarvis Roadmap
JARVIS ROADMAP
Jarvis is the human-agent collaboration and learning-loop protocol. It defines WorkSession, Policy, Request, Review, Takeover, Contribution, EvidenceManifest, LearningRecord, MemoryProposal, and SkillProposal so existing agents and host products can collaborate with humans without replacing their runtimes.
Near-term priority: prove one v0 protocol loop end to end: protocol lock, schemas, version and capability negotiation, adapter contract, first host POC mapping, portable export, and conformance fixtures. Keep scope narrow: protocol records first, one product host plus one CLI/existing-agent wrapper, evidence and learning captured during work.
Timing |  | Protocol Lock |  | Schemas + Adapters |  | Proof + Review
Week | Date range | Primary goal | Protocol lock + research | Schemas + conformance | Adapter + interoperability | Host POC + demo | Done when
Now | Jun 2-5 | Turn Jarvis into an implementation-ready protocol lock. | - freeze v0 protocol lock - align README, principles, architecture, roadmap - keep language direct and host-generic - confirm object names and lifecycle | - define schema entry gate - list open schema questions - identify version, capability, extension, and error-model gaps - prepare schema folder layout | - name first adapter targets - define what an existing agent must expose - map agent steps to JarvisEvent - map blocked action to Request | - choose first product host proof - choose one CLI/external-agent wrapper - define host-private fields that stay out of export - define demo success path | Protocol lock is the source for schema work, first host and wrapper targets are named, and no new runtime/product assumptions enter Jarvis.
W1 | Jun 8-12 | Create the v0 machine-readable contract. | - finalize required object meanings - lock WorkSession state transitions - lock Request, Review, Takeover states - lock Contribution and Evidence terms | - create JSON schemas for core objects - create JarvisEvent envelope schema - create portable export schema - define protocol error codes | - draft adapter contract - define AgentWorker wrapper surface - define tool/action to PolicyDecision mapping - define limitations field for unsupported concepts | - create first host mapping table - define host WorkSession flow - define Request inbox behavior - define Review and Takeover capture points | A developer can read the schemas and know exactly how to create a valid WorkSession, Request, Review, Contribution, EvidenceManifest, and LearningRecord.
W2 | Jun 15-19 | Make conformance strong enough to prove compatibility. | - write compatibility rules - define extension namespace rules - define version negotiation - define capability negotiation | - build golden-path fixtures - build failing fixtures - validate status transitions - validate export does not require host-private fields | - create CLI/existing-agent wrapper plan - capture messages/actions as JarvisEvents - capture tool use as PolicyDecision and Evidence - capture human correction as Review | - run host POC mapping against schemas - generate sample WorkSession export - show evidence and learning records - document host-only assumptions separately | Conformance rejects missing policy, missing review, stale takeover continuation, unattributed contribution, weak evidence, and silent learning mutation.
W3 | Jun 22-26 | Prove Jarvis with the first host and one existing-agent wrapper. | - refine protocol from real fixture pain - keep object names stable - document compatibility decisions - update protocol lock only for real contradictions | - run schemas against host export - run schemas against CLI/wrapper export - compare both exports for same core semantics - record gaps as conformance issues | - implement wrapper proof path - HumanWorker objective -> AgentWorker action - blocked action -> Request - human response -> Review or Takeover | - demonstrate host POC flow - export EvidenceManifest - export LearningRecord - show human, agent, and pair learning - update simulation narrative if needed | Two different host shapes produce valid Jarvis records for the same collaboration loop without sharing runtime, UI, storage, or execution stack.
W4 | Jun 29-Jul 3 | Freeze v0.1 alpha and prepare team/public review. | - close protocol lock gaps - publish compatibility notes - summarize decisions and non-goals - prepare v0.2 evidence/learning backlog | - freeze v0.1 schema draft - publish conformance checklist - publish valid/invalid examples - define migration policy draft | - write adapter guide - document CLI/existing-agent wrapper - document host implementation guide - identify next two adapter targets | - publish final demo URL - package host POC evidence - prepare team walkthrough - collect review notes into next-cycle issues | Jarvis has a v0.1 alpha package of protocol docs, schemas, examples, conformance fixtures, one host proof, and one existing-agent wrapper proof.
Later | After v0.1 | Expand only from conformance and proof-host evidence. | - harden object model from real adapters - add migration rules - add public implementation checklist - prepare v0.2 evidence and learning beta | - richer EvidenceManifest - stronger Contribution taxonomy - review-state workflows - memory and skill compatibility rules | - more agent wrappers - MCP/A2A/AG-UI integration notes - SDK-neutral adapter examples - compatibility badges | - additional host proofs - public demo refresh - team onboarding sheet - protocol review sessions | Expansion is justified by valid exports, conformance failures, adapter pain, and host proof evidence, not by adding features from vibes.