## Jarvis Roadmap
JARVIS ROADMAP
Jarvis is the human-agent collaboration and learning-loop protocol. It defines Worker, Actor, HumanWorker, AgentWorker, WorkSession, JarvisEvent, Policy, PolicyDecision, Request, Review, Takeover, Contribution, EvidenceManifest, LearningRecord, MemoryProposal, SkillProposal, and OutcomeReport so existing agents and host applications collaborate with humans without replacing their runtimes.
Near-term priority: maintain the v0.1.0 Protocol Alpha contract and define next-phase protocol targets after acceptance review. Keep scope narrow: protocol records first, OpenAPI contract second, conformance third, compatibility mapping fourth, compatible example last.
Timing |  | Protocol Lock |  | OpenAPI + Conformance |  | Compatibility Proof
Week | Date range | Primary goal | Protocol lock + research | OpenAPI + conformance | Compatibility + interoperability | Compatible example | Done when
Now | Jun 2-5 | Turn Jarvis into an implementation-ready protocol lock. | - freeze v0.1 protocol lock - align README, principles, architecture, roadmap - keep language direct and host-generic - confirm object names and lifecycle | - define OpenAPI entry gate - list open OpenAPI questions - identify version, capability, extension, and error-model gaps - prepare OpenAPI component and path layout - define zero-trust headers, security scheme, and header parameters | - defer integration implementation - name compatibility questions only - preserve runtime independence | - keep host implementation work out of active scope - define compatible-example prerequisites only | Protocol lock is the source for OpenAPI work, OpenAPI 3.1 is the machine-readable communication contract, and no compatible example enters this week.
W1 | Jun 8-12 | Create the v0.1 OpenAPI communication contract. | - finalize required object meanings - lock WorkSession state transitions - lock Request, Review, Takeover states - lock Contribution and Evidence terms | - create OpenAPI 3.1 document skeleton - create components.schemas for core objects - create path layout for core operations - define protocol error responses - define required security headers | - document compatibility mapping questions - define AgentWorker compatibility surface - define tool/action to PolicyDecision mapping - define limitations field for unsupported concepts | - keep host implementation work out of active scope - define compatible-example gate conditions only | A developer reads the OpenAPI contract and knows exactly how to create a valid WorkSession, Request, Review, Contribution, EvidenceManifest, and LearningRecord.
W2 | Jun 15-19 | Make conformance strong enough to prove compatibility. | - write compatibility rules - define extension namespace rules - define version negotiation - define capability negotiation | - build golden-path fixtures - build failing fixtures - validate status transitions - validate export does not require host-private fields | - create existing-agent compatibility plan - capture messages/actions as JarvisEvents - capture tool use as PolicyDecision and Evidence - capture human correction as Review | - keep compatible example out of active scope - record compatible-example prerequisites from conformance only - generate protocol-only sample WorkSession export - document host-only assumptions separately | Conformance rejects missing policy, missing review, stale takeover continuation, unattributed contribution, weak evidence, and silent learning mutation.
W3 | Jun 22-26 | Prove Jarvis with conformance fixtures and protocol compatibility mapping. | - refine protocol from real fixture pain - keep object names stable - document compatibility decisions - update protocol lock only for real contradictions | - run OpenAPI examples against host export - run OpenAPI examples against second compatible export - compare both exports for same core semantics - record gaps as conformance issues | - define proof compatibility path - HumanWorker objective -> AgentWorker action - blocked action -> Request - human response -> Review or Takeover | - prepare compatible examples after the conformance gate - define host-private fields that stay out of export - update simulation narrative if needed | Two compatible implementation shapes produce valid Jarvis records for the same collaboration loop without sharing runtime, UI, storage, or execution stack.
W4 | Jun 29-Jul 3 | Close v0.1.0 Protocol Alpha and prepare compatible-example review. | - close protocol lock gaps - publish compatibility notes - summarize decisions and non-goals - prepare v0.2 evidence/learning backlog | - freeze v0.1 OpenAPI contract - publish conformance checklist - publish valid/invalid examples - define migration policy draft | - write compatibility mapping guide - document CLI/existing-agent compatibility mapping - document compatible implementation guide - identify next two compatibility targets | - publish protocol proof walkthrough URL - package compatible-example readiness notes - prepare team walkthrough - collect review notes into next-cycle issues | Jarvis has a v0.1.0 Protocol Alpha package of protocol docs, OpenAPI contract, examples, conformance fixtures, compatible-example readiness, and one existing-agent compatibility mapping.
Later | After v0.1 | Expand only from conformance results and compatible-example evidence. | - harden object model from real compatible implementations - add migration rules - add public implementation checklist - prepare v0.2 evidence and learning beta | - richer EvidenceManifest - stronger Contribution taxonomy - review-state workflows - memory and skill compatibility rules | - more agent compatibility mappings - MCP/A2A/AG-UI integration notes - SDK-neutral compatibility examples - compatibility evidence labels and claim-format examples - no certification or adopter badge | - additional compatible examples - public proof refresh - team onboarding sheet - protocol review sessions | Expansion is justified by valid exports, conformance failures, compatibility pain, and compatible-example evidence, not by unproven feature expansion.